ANNUAL SEE PARLIAMENTARY PROGRAMME 2013-2014

| GOALS | ACTIONS | TIME FRAME | PARTNERS |
| --- | --- | --- | --- |
| 1. Institutional building and strengthening of coordination and communication activities of the SEECP PD |  |  |  |
| 1.1 Transformation and institutionalization of SEECP PD into The Parliamentary Assembly (SEECP PA ). | 1. Preparing the documents necessary for the convening of the Inaugural session of the SEECP PA | July 2013- June 2014 | CiO, RSPC SEE, National Parliaments |
|  | 2. Strengthening coordination and exchange of information through the network of national coordinators | July 2013- June 2014 | RSPC SEE, National Parliaments |
|  | 3 Organizing the Inaugural session of the SEECP PA | May-June 2014 | CiO, RSPCSEE |
| 1.2. Promotion of the mission, vision and basic guidelines of the SEECP PA. | 1. Preparing media and public events and distributing press-materials | May-June 2014 | CiO, Troika |
| 2.Developing interaction of SEECP parliaments on important regional issues |  |  |  |
| 2.1 Defining and promoting priority areas for cooperation at parliamentary level | 1. Support the CiO priorities through active participation in organized events | July 2013 – June 2014 | CiO, RSPC SEE, National Parliaments |
|  | 2. Carrying out research on possible fields of cooperation in a long-term perspective | July 2013 – December 2013 | RSPC SEE, National Parliaments |
|  | 3. Identifying regional and international partners and donors | December 2013 – June 2014 | RSPC SEE |
| 2.2 Introducing sustainable mechanisms for exchange of information and legislative experience | 1. Continuing exchange of experiences and good practices of the Parliaments, Independent Regulatory Bodies and CSOs of the SEECP countries. Establishment of networks of Independent Regulatory Bodies in SEECP countries | July 2013 – June 2014 | RSPC SEE, National parliaments, Independent Regulatory Bodies, CSOs |
|  | 2. Establishing cooperation with Cetinje Parliamentary Forum and COSAP | July 2013 – December 2013 | RSPC SEE, Cetinje Parliamentary Forum, COSAP |
| 3.Enhancing coordination between Parliamentary and Governmental Dimensions of the SEECP |  |  |  |
| 3.1 Deepening cooperation with RCC | 1.Support the implementation of RCC Strategy and Work Program 2014-2016 | July 2013 – June 2014 | RSPC SEE, RCC Secretariat, National parliaments |
|  | 2. Organizing joint events | July 2013 – June 2014 | RSPC SEE, RCC Secretariat |
| 3.2 Involving the SEECP Parliamentary Dimension in SEE 2020 Strategy drafting and implementation | 1. Participation in the development of SEE 2020 Strategy and outlining the role of SEECP Parliamentary Dimension | July 2013 – June 2014 | RCC Secretariat, RSPCSEE, SEE Regional Initiatives, National parliaments, |
|  | 2. Developing working relations with SEE Regional Initiatives responsible for SEE 2020 drafting and implementation | July 2013 – June 2014 | RCC Secretariat, RSPCSEE, SEE Regional Initiatives, National parliaments |
| 4.Strengthening relations with EU institutions and promotion of the European perspective of the region |  |  |  |
| 4.1 Strengthening cooperation with European Parliament | 1. Visit of SEECP parliamentary delegation to EP and other EU institutions. | February/March 2014 | RSPC SEE, RCC Liaison office in Brussels, Directorate-General for External Policies of the EP |
|  | 2. Organizing joint events | July 2013 – June 2014 | RSPC SEE, Directorate-General for External Policies of the EP and Directorate for Relations with National Parliaments |
|  | 3. Contributing to the agenda and organization of the seminars for Western Balkan Parliaments. | July 2013 – June 2014 | RSPC SEE, Directorate-General for External Policies of the EP |
| 4.2 Active presentation of Europe 2020 and SEE 2020 Strategies values and agenda | 1. Organizing Youth Essay Writing Contest “See SEE in 2020” | October 2013 – May 2014 | RSPC SEE, National Parliaments, partner organizations |
| 5. Improving cooperation and setting up of joint initiatives with regional and international parliamentary organizations |  |  |  |
| 5.1 Strengthening cooperation with regional and international parliamentary organizations | 1. Continuing cooperation with the Baltic Assembly | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |
|  | 2. Applying for observer status at the Baltic Sea Parliamentary Conference | July 2013 – June 2014 | CiO, Troika, RSPC SEE, national parliaments |
|  | 3. Maintaining exchange of information with the Benelux parliament | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |
|  | 4. Continuing cooperation with GUAM PA | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |
| 5.2. Creating new partnerships and prospects for joint activities | 1. Starting cooperation with PACE | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |
|  | 2. Organizing study visit to PABSEC | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |
|  | 3. Establishing working contacts with Parliamentary Assembly of the Mediterranean | July 2013 – June 2014 | CiO, Troika, RSPC SEE, National parliaments |

This Programme will be in force until the Inaugural Session of the SEECP PA